AktivAsia

Training Plan & Participant Lifecycle Automation

Email copy for Zoho Flow automation — Country Team & Participant reminders

- Training Cycle & Automation Timeline (Recommended)[1]

- Total preparation time to training day: approximately 8 to 9 weeks. Each automated reminder is anchored to a milestone below.

- 9 weeks out  —  Form Creation and Other Supporting Documents   → C1 / Associate Training

- 8 to 7 weeks out  —  Advertising and Application Window + Logistic Prep   → C2 (share application link)

- 6 to 5 weeks out  —  Screening and Selection   → C3 (begin selecting / rejecting)

- 4 weeks out  —  Communication of Results   → C4 (confirm final list)

- 3 to 1 weeks out  —  Pre-Training Preparation (logistics + content)   → Logistics reminder

- 0 weeks  —  Training   → C5, then C6, then P1 / P2 (6-month)

The old fixed "15 days out" trigger has been retired. All country-team reminders (C1 to C6) now re-anchor to these milestones off the training start and end dates, so if a training date moves, every reminder shifts with it automatically.

Country Team Reminders

C1  Training Plan check-in (sent 1st of every month)

Subject: 📋 {{Country}}: Here's where your {{Year}} Training Plans stand

Dear {{Country_Team_Name}},[1]

A new month is here, so here's a quick look at your Training Plans for {{Year}} that haven't yet commenced:

{{Training_Plans_List}} (e.g. Training Name | Planned Month | Status)

If any of these is now confirmed and going ahead soon, please fill out the form below to trigger it in our system. This is what officially associates it with an approved Training Plan and gets everything moving on our end. 🚀

Associate a confirmed training here: {{Associate_Training_Form_Link}}

If nothing is confirmed yet, no action is needed. We'll check in again next month.[2]

With thanks,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

Build note: {{Training_Plans_List}} needs a Deluge loop pulling unconfirmed Training Plan records for the year into a simple HTML list before send.

C2  Pre-training reminder (open applications early)

Subject: 📅 Applications open: {{Training_Name}} on {{Start_Date}}

Dear {{Country_Team_Name}},

A heads-up that applications for {{Training_Name}} should be opening now, ahead of the training on [1] {{Start_Date}}. 🗓️

Ideally applications open 8 to 7 weeks out, with a 1 to 2 week window and screening at 6 to 5 weeks, so there is enough time to advertise and choose well. Here is the application link, ready for you to share with your prospective participants:

{{Application_Form_Link}}

Feel free to circulate this through your usual channels. If anything about the training details changes in the meantime, just update it in Zoho as usual.

With thanks,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

Build note: Trigger this 8 to 7 weeks before the training start date (not 15 days), aligned to the recommended Training Cycle timeline, so teams have the full advertising and application window. No confirmation action required, informational plus the application link.

C3  7-day pre-training reminder

Subject: ⏰ One week out: {{Training_Name}} and your participant list

Dear {{Country_Team_Name}},

{{Training_Name}} is now just one week away, starting {{Start_Date}}. ✅

Please double-check the training details in Zoho are accurate: dates, venue, facilitators, and focus.

If you're still gathering applicants, here's the application link to keep sharing:

{{Application_Form_Link}}

And once applicants are in, you can begin selecting or rejecting them here:

{{Participant_Selection_Form_Link}}

The sooner this list takes shape, the smoother the run-up to training day will be.

With thanks,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

C4  Participant confirmation (5 to 1 days before training)

Subject: ✅ Action needed: confirm your participant list for {{Training_Name}}

Dear {{Country_Team_Name}},

{{Training_Name}} begins on {{Start_Date}}. Before it starts, we need your final participant list locked in. 📝

Please go through your applicants in Zoho and make sure each one is marked correctly. Everyone currently in the Applied stage needs to move to either Selected or Rejected.

Review and update your list here: {{Participant_Selection_Form_Link}}

Please complete this before the training begins. A clean, confirmed list means accurate records and a smoother evaluation process afterwards.

With thanks,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

Build note: Consider sending once at day 5, then only re-sending if applicants remain in the Applied stage, rather than daily for all five days.

C5  Training end date (Selected → Graduated, post-eval, Drive upload)

Subject: 🎓 {{Training_Name}} complete: confirm participants and next steps

Dear {{Country_Team_Name}},

{{Training_Name}} has now finished. Thank you for all the work that went into delivering it! 🙌

A few things we need from you to close it out properly:

1. Confirm your final participant list.

Everyone who completed the training should move from Selected to Graduated or Post Evaluation Completed, so our records reflect who actually took part.{{Participant_Confirmation_Form_Link}}

2. Share the post-training evaluation form

with your participants and encourage them to complete it. Their feedback matters a great deal to us.{{Post_Training_Eval_Form_Link}}

3. Upload your training photos

to this folder so we can use them for reporting and stories. 📸{{Google_Drive_Link}}

With thanks and solidarity,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

C6  Post-eval nudge to country team (7 days after training end)

Subject: 🔔 Following up: post-training evaluations for {{Training_Name}}

Dear {{Country_Team_Name}},

It's been a week since {{Training_Name}} finished, and we wanted to follow up on the post-training evaluations.

If some participants haven't yet completed the form, a gentle nudge from you goes a long way. Their responses help us understand what worked and where we can do better.

Form link to share again: {{Post_Training_Eval_Form_Link}}

Still have photos to upload? Add them here: {{Google_Drive_Link}} 📸

With thanks,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

Participant Reminders

P1  6-month post-evaluation (daily, until deadline)

Subject: 💭 A few minutes for your Impact Evaluation, {{Participant_First_Name}}[2] [3]

Dear {{Participant_Name}},

It's been half a year since the {{Training_Name}} training wrapped up, and we've been thinking about you and wondering how things have unfolded on your end. 🌱

We'd love to hear what you've been up to. Since we last saw you, have you run a campaign you're proud of? Brought new people in, shifted something that felt stuck, raised support, or passed on what you learned to others? Whether it's been a season of big wins or slow, stubborn progress, your story matters to us.

That's what this check-in is really about. We reach out at the half-year and one-year marks to understand the longer-term difference the training makes in the real work you're doing, and honestly, your answers are what tell us whether any of this is landing. They shape how we support graduates like you and what we build next.

The form takes about 10 to 15 minutes. Please complete it within one week of receiving this email, and no later than {{Deadline_Date}}.

If you feel more comfortable answering in your own language, please do. You can also use the translate option in Google Chrome: right-click on the page and select your preferred language.

And if there's anything you'd like to share beyond the form, a story, a question, or just an update, reach out any time. We'd genuinely love to hear from you.

Complete your form here: {{Impact_Eval_Form_Link}}

With gratitude and solidarity,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact regional@aktivasia.org.

Build note: Wire a stop condition on form submission so participants don't receive seven emails in a row after responding.

P2  6-month post-evaluation, overdue (weekly)

Subject: ⏳ Still open: your Impact Evaluation Form, {{Participant_First_Name}}

Dear {{Participant_Name}},

We're reaching out again about your Impact Evaluation Form for the {{Training_Name}} training.

The deadline was {{Deadline_Date}}, and while it has now passed, the form is still open and we would very much value your response. 🙏

It only takes a few minutes, and your feedback genuinely helps us improve our programming and support future participants.

If you feel more comfortable answering in your own language, please do. You can also use the translate option in Google Chrome: right-click on the page and select your preferred language.

Complete your form here: {{Impact_Eval_Form_Link}}

Thank you, and we hope you're well.

With gratitude and solidarity,

AktivAsia Regional Team

This is a system-generated email. For any concerns, please contact gino@aktivasia.org.

Build note: Wire a stop condition on form submission so participants don't receive overdue email in a row after responding.